## RICE Backlog
Rank | ID | Story | Reach (1-10) | Impact (1-5) | Confidence | Effort (person-months) | RICE Score | Rationale
1 | S6 | Agent-side causation view — CS agent sees causation breakdown on inbound call | 3 | 3 | 100% | 3 | 3 | Highest confidence (deterministic data display, no AI uncertainty) and lowest effort — immediate operational win for call centre deflection
2 | S1 | Premium explanation — policyholder receives causal breakdown with renewal notice | 10 | 5 | 50% | 9 | 2.78 | Highest reach and impact of any story (every policyholder, every renewal), but confidence is capped at 50% because value depends on A/B test validation and Phase 0 data readiness — this is the core value hypothesis
3 | S7 | A/B test cohort isolation — controlled experiment validating churn impact before full rollout | 2 | 5 | 80% | 3 | 2.67 | Low reach (single experiment cohort, limited duration) but maximum impact per policy touched — validates or invalidates the entire EUR 450K–2.5M value hypothesis at EUR 80K test cost
4 | S2 | Batch personalisation at scale — 500K notices generated within the print window | 3 | 4 | 80% | 5 | 1.92 | Operational enabler for S1 at scale — well-understood engineering problem with 80% confidence; without it, personalised comms don't ship beyond pilot
5 | S4 | Compliance rule engine pre-flight — market-specific regulatory checks before dispatch | 3 | 4 | 80% | 5 | 1.92 | Regulatory gate for S1 and S10 — no notice can be dispatched without passing market-specific rules; prevents the RACQ/ASIC scenario (570K misleading notices)
6 | S10 | Multi-language notice generation — EN, DE, FR, IT, ES from a single pipeline | 3 | 3 | 80% | 4 | 1.8 | Enables multi-market deployment; well-understood localisation pattern with pre-approved LLM prompts per language
7 | S3 | Fair-value evidence trail — auditable pricing attribution per renewal for regulator requests | 2 | 4 | 80% | 4 | 1.6 | Regulatory requirement with direct DORA/FCA implications; low reach (compliance team + occasional regulator requests) but high impact on legal defence
8 | S8 | Phase 0 data readiness audit — discovers which rating variables are exposed vs opaque per market | 1 | 5 | 80% | 3 | 1.33 | Gating prerequisite for S1, S3, S5 — without this, no personalised comms are possible; one-time effort with outsized downstream impact
9 | S5 | Conversational 'why?' follow-up — policyholder can ask follow-up questions in natural language | 4 | 3 | 50% | 6 | 1 | Value-add on top of S1 — only ~20% of policyholders expected to use it; confidence at 50% due to AI-dependent conversation quality and regulatory acceptance uncertainty
10 | S9 | Sentiment-driven retention escalation — flags inbound calls showing switching intent | 2 | 2 | 50% | 4 | 0.5 | Lowest RICE — sentiment detection accuracy varies widely; only triggered for a subset of calls where customer is already contact centre; requires CRM integration
ADVERSARIAL CRITIQUE
Lowest-confidence row critique
S1 (Premium explanation — 50% confidence): The 50% confidence is doing too much work. It conflates three independent risks: (a) A/B test validates churn reduction (uncertain), (b) Phase 0 achieves ≥70% attribution in ≥3 markets (uncertain), (c) LLM-generated causation text is accurate and regulator-acceptable (uncertain). Each has a different probability; lumping them as '50%' masks which one is the binding constraint. Suggested split: decompose confidence into sub-scores per dependency and re-score as the minimum of the three. If Phase 0 confidence is 80% but regulatory acceptance is 30%, the effective confidence is 30%, not 50%. This would drop S1 below S7 and S6 in RICE ranking — which is the correct signal for where to invest risk-reduction effort first.
Highest-score row critique
S6 (Agent-side causation view — RICE 3.0): S6 scores highest because Reach×Impact/Effort is favourable (3×3×1.0/3 = 3.0). But this masks a dependency problem: S6 requires S1's causation data to exist before the agent can display it. If S1 hasn't been built, S6 displays nothing. The RICE score treats S6 as independent when it is fully gated on S1. This inflates S6's score by ~2x. Two options: (a) re-score S6 as a dependency of S1 (RICE = 0 until S1 ships), or (b) scope S6 as a 'Phase 0 results viewer' that shows attribution coverage per market rather than per-policy causation — different story, different score. Recommended: Option (b) stays in the backlog as presented, but add a dependency column so the ranking surface shows which stories block which.