## Impact x Effort
Cluster | Origin Ideas | Consolidated Idea | Category | Impact (1-5) | Effort (1-5) | Priority Score (I-E) | Rationale | Quadrant
Cluster 1 | A1 + A3 | Confidence-aware availability signal on product page — show estimated likelihood (%) with freshness indicator ('checked X min ago') and one-line explainer of recent sell-through velocity | Product page UX | 5 | 3 | 2 | Core intervention. Replaces binary 'In stock' with calibrated estimate. Sets expectations, contains disappointment even when wrong. Low effort for UX change; model already exists. **Highest ROI of any cluster.** | DO FIRST
Cluster 2 | A2 | Optional real-time staff ping ('Check before you commit') — shopper taps to send immediate handheld request; staff responds yes/no within 2 min; item held if confirmed | Pre-purchase verification | 4 | 4 | 0 | Powerful for risk-averse shoppers but adds real-time staff dependency. Requires handheld integration, staff training, and SLA management. Build after Cluster 1 proves value. | DO NEXT
Cluster 3 | C1 + C3 | Staff confirmation hold — when staff confirms via handheld, item is physically badged ('Held for C&C') and stored on a designated shelf; hold window adapts dynamically based on store traffic (peak=1h, off-peak=4h) | Operational hold workflow | 5 | 3 | 2 | Eliminates phantom stock for confirmed items entirely. Low-tech badge system works with existing handheld flow. Dynamic hold balances customer convenience with store capacity. | DO FIRST
Cluster 4 | B1 + B3 | Proactive alternative fulfilment offer — when first-choice store can't confirm, system auto-checks nearest alternative stores with confirmed stock and offers one-tap re-route; extended with 'shopper in transit' pre-arrival check | Error recovery | 4 | 3 | 1 | Captures orders that would otherwise cancel (~7% recovery). 'In transit' timer prevents wasted trips mid-journey. Depends on Cluster 3 data (confirmed stock at alternative store). | DO NEXT
Cluster 5 | B2 | Store-level discrepancy dashboard — real-time feed of 'items promised to online shoppers but not yet picked' per store, colour-coded by status (confirmed / unpicked / can't-find) | Staff operations | 3 | 3 | 0 | Internal ops tool. Doesn't directly improve customer experience but enables staff to proactively resolve discrepancies. Useful once C&C volume justifies dedicated dashboard. | DO LATER
Cluster 6 | C2 | Post-collection 'Did you find it?' micro-survey — single-tap feedback ('Yes / No — shelf was empty / No — couldn't find it'); response feeds confidence model as training signal per store+SKU+time | Feedback loop | 2 | 1 | 1 | Lowest effort (single-tap survey, negligible engineering). Low immediate impact but compounds as model learns. Build as a background task — no dependencies, ship early. | DO NOW (background)
QUADRANT MAP
| Low Effort (1-2) | Medium Effort (3) | High Effort (4-5)
High Impact (4-5) | Cluster 6 — Micro-survey | Cluster 1 — Confidence signal Cluster 3 — Staff hold Cluster 4 — Proactive recovery | Cluster 2 — Pre-check ping
Medium Impact (3) |  | Cluster 5 — Staff dashboard
Low Impact (1-2)
CLUSTERING & DE-DUP RECORD
Clusters formed | 9 raw ideas → 6 clusters | Merged A1+A3 (both are product-page availability signals — A1 uses abstraction, A3 uses raw data; implement as configurable display of the same model). Merged C1+C3 (both are hold-window mechanisms — physical badge + dynamic timer). Merged B1+B3 (both are recovery paths — B1 fires after ping, B3 fires mid-travel).
Duplicates eliminated | 3 merges (9→6) | A1+A3: same data, different display. C1+C3: same hold process, different time policy. B1+B3: same recovery trigger, different delivery timing.
Unchanged (singletons) | 3 standalone clusters | A2 (dual throttle — pre-check workflow is distinct from the confidence signal). B2 (staff dashboard — internal tool, different user and UX). C2 (micro-survey — feedback loop, different purpose and timing).
PRIORITY DEFINITIONS
DO FIRST (Green) | Build now. Core to the value proposition. High impact, manageable effort.
DO NEXT (Blue) | Build after DO FIRST proves value. Depends on DO FIRST data or infrastructure.
DO LATER (Yellow) | Build when scale justifies it. Internal ops tool — not customer-facing.
DO NOW background (Orange) | Build immediately but as background task. Negligible effort, compounds over time.